## 표지
SKN14 AI Family camp Final Project Team4 WBS
Team name | 4-seed[포-시드]
Project Manager | 조성렬
Subject | LLM 활용 인공지능 인플루언서 - 나만의 버추얼 인플루언서 만들기 (서비스명: VogueMe)
Period | 2025.8.11 ~ 2025.10.2

## WBS with Gantt Chart
[9 empty] | PHASE 1 | [20 empty] | PHASE 2 | [20 empty] | PHASE 3
[9 empty] | 기획/시스템 설계 | [6 empty] | Sprint 1 | [6 empty] | 중간발표: 8월 26일 | [6 empty] | Sprint 2 | [13 empty] | Sprint 3 | [13 empty] | 최종발표: 10월 2일
Issue Link | WBS NUMBER | 업무명 | 담당자 | 계획 |  | 소요일 | 진행상태 | 완료율(%) | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8
|  |  |  | 시작 | 완료 |  |  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5
| 1 | 프로젝트 정의 및 업무 계획 | time axis 2025-08-11 to 2025-10-05
| 1.1 | 문제 정의 및 구체화 | 전원 | 2025-08-11 | 2025-08-21 | 9 | Done | time axis 2025-08-11 to 2025-10-05
| 1.1.1 | ⎿데스크리서치 | 전원 | 2025-08-11 | 2025-08-21 | 9 | Done
https://github.com/skn-ai14-250409/SKN14-Final-4Team/issues/8 | 1.1.2 | ⎿프로젝트 기획서 작성 | 윤이서 | 2025-08-20 | 2025-08-21 | 2 | Done | time axis 2025-08-11 to 2025-10-05
| 1.2 | 업무 계획 | 전원 | 2025-08-27 | 2025-08-31 | 3 | Done
https://github.com/skn-ai14-250409/SKN14-Final-4Team/issues/6 | 1.2.1 | 요구사항명세서 작성 | 조성렬 | 2025-08-28 | 2025-08-28 | 1 | Done | time axis 2025-08-11 to 2025-10-05
https://github.com/skn-ai14-250409/SKN14-Final-4Team/issues/7 | 1.2.2 | WBS 작성 | 조성렬 | 2025-08-28 | 2025-08-28 | 1 | Done | time axis 2025-08-11 to 2025-10-05
| 2 | 분석 및 설계 | time axis 2025-08-11 to 2025-10-05
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=124645899&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C15 | 2.3 | DB 설계 | 송지훈 | 2025-08-28 | 2025-08-28 | 1 | Done | time axis 2025-08-11 to 2025-10-03
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126119954&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C60 | 2.3.1 | ⎿ERD 작성 | 송지훈 | 2025-08-28 | 2025-08-28 | 1 | Done | time axis 2025-08-11 to 2025-10-03
| 2.3.2 | ⎿테이블 정의서 작성 | 송지훈 | 2025-08-28 | 2025-08-28 | 1 | Done | time axis 2025-08-11 to 2025-10-03
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=124646493&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C17 | 2.4 | 화면 설계 | 윤이서 | 2025-08-27 | 2025-08-29 | 3 | Done | time axis 2025-08-11 to 2025-10-05
https://github.com/orgs/skn-ai14-250409/projects/70/views/2?pane=issue&itemId=126119994&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C61 | 2.4.1 | ⎿시스템 아키텍처 다이어그램 | 송지훈 | 2025-08-27 | 2025-08-27 | 1 | Done | time axis 2025-08-11 to 2025-10-03
https://github.com/orgs/skn-ai14-250409/projects/70?pane=issue&itemId=126186622&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C70 | 2.4.2 | ⎿메뉴 구조도 | 윤이서 | 2025-08-27 | 2025-08-28 | 2 | Done | time axis 2025-08-11 to 2025-10-03
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=124646523&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C18 | 2.4.3 | ⎿와이어프레임 | 윤이서 | 2025-08-27 | 2025-08-29 | 3 | Done | time axis 2025-08-11 to 2025-10-03
https://github.com/orgs/skn-ai14-250409/projects/70/views/2?pane=issue&itemId=3359231190&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C67 | 2.4.4 | ⎿플로우차트 | 윤이서 | 2025-08-27 | 2025-08-29 | 3 | Done
| 3 | 데이터 수집 및 저장 | time axis 2025-08-11 to 2025-10-05
| 3.1 | 가상 피드 생성용 이미지 수집 | 공지환, 조성렬 | 2025-08-13 | 2025-08-20 | 6 | Done | time axis 2025-08-11 to 2025-10-05
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=124646585&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C19 | 3.1.1 | ⎿인플루언서 이미지 수집 | 공지환 | 2025-08-13 | 2025-08-19 | 5 | Done | time axis 2025-08-11 to 2025-10-03
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=124647293&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C20 | 3.1.2 | ⎿배경 이미지 수집 | 조성렬 | 2025-08-13 | 2025-08-19 | 5 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=124647390&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C21 | 3.1.3 | ⎿브랜드별 ootd 이미지 수집 | 조성렬 | 2025-08-13 | 2025-08-20 | 6 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126096981&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C43 | 3.2 | 친환경 브랜드 제품 데이터 수집 | 조성렬 | 2025-08-27 | 2025-08-29 | 3 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126174035 | 3.2.1 | ⎿브랜드 선정 | 조성렬 | 2025-08-27 | 2025-08-27 | 1 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126174394&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C63 | 3.2.2 | ⎿웹스크래핑 | 조성렬 | 2025-08-27 | 2025-09-01 | 4 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126174612&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C64 | 3.2.3 | ⎿데이터 정제 | 조성렬 | 2025-08-28 | 2025-09-01 | 3 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126176880&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C66 | 3.2.3 | ⎿RDB 구축(CRUD) | 조성렬 | 2025-08-29 | 2025-09-01 | 2 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126096216&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C42 | 3.3 | 콘텐츠 자막 수집 | 윤이서 | 2025-09-01 | 2025-09-03 | 3 | Done | time axis 2025-08-11 to 2025-10-03
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126117670&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C49 | 3.3.1 | ⎿콘텐츠 선정 및 링크 수집 | 윤이서 | 2025-09-01 | 2025-09-01 | 1 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126175183&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C65 | 3.3.2 | ⎿자막 다운로드 및 정제 | 윤이서 | 2025-09-02 | 2025-09-03 | 2 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126117720&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C50 | 3.3.3 | ⎿임베딩 및 벡터DB 구축 | 윤이서 | 2025-09-03 | 2025-09-03 | 1 | Done
| 4 | 중간 발표 | time axis 2025-08-11 to 2025-10-05
https://github.com/orgs/skn-ai14-250409/projects/70/views/2?pane=issue&itemId=124650220&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C24 | 4.1 | 중간 발표 PT 자료 준비 | 윤이서 | 2025-08-25 | 2025-08-26 | 2 | Done | time axis 2025-08-11 to 2025-10-05
| 5 | 데이터 전처리 및 모델 학습 | time axis 2025-08-11 to 2025-10-05
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=125464428&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C34 | 5.1 | TTS Fine-tuning용 데이터 수집 | 공지환, 송지훈, 윤이서 | 2025-08-22 | 2025-09-05 | 11 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126101581&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C46 | 5.1.1 | ⎿myshell-ai/MeloTTS-Korean, facebook/mms-tts-kor | 공지환 | 2025-08-25 | 2025-08-29 | 5 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126101701&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C47 | 5.1.2 | ⎿SparkAudio/Spark-TTS-0.5B | 송지훈 | 2025-08-22 | 2025-08-29 | 6 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126101883&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C48 | 5.1.3 | ⎿coqui-ai/TTS, GPT-SoVITS | 윤이서 | 2025-08-22 | 2025-09-05 | 11 | Done
| 6 | LLM 모델링 및 평가 | time axis 2025-08-11 to 2025-10-05
| 6.1 | LLM 테스트 계획 | 전원 | 2025-09-01 | 2025-09-12 | 10 | Done | time axis 2025-08-11 to 2025-10-03
| 6.2 | LLM 모델 선정 - openAI | 전원 | 2025-09-01 | 2025-09-12 | 10 | Done | time axis 2025-08-11 to 2025-10-03
https://github.com/orgs/skn-ai14-250409/projects/70/views/2?pane=issue&itemId=126894456 | 6.3 | FastAPI 파이프라인 구성 | 윤이서 | 2025-09-02 | 2025-09-02 | 1 | Done
| 6.4 | RAG 구축 | 윤이서, 조성렬, 공지환 | 2025-09-01 | 2025-09-12 | 10 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126286689&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C72 | 6.4.1 | ⎿VectorDB 유사도 검색 및 | 윤이서 | 2025-08-28 | 2025-08-28 | 1 | Done | time axis 2025-08-11 to 2025-10-03
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126286706&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C73 | 6.4.2 | ⎿LLM 생성 테스트(output: SQL쿼리) | 윤이서 | 2025-08-29 | 2025-08-29 | 1 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126286719&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C74 | 6.4.3 | ⎿LLM생성 결과 RDB 조회 테스트 | 조성렬 | 2025-08-28 | 2025-09-01 | 3 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/2?pane=issue&itemId=126744148 | 6.4.5 | ⎿조회된 제품과 JSON을 활용한 LLM 코멘트 생성 | 공지환 | 2025-09-01 | 2025-09-02 | 2 | Done
| 7 | Front-end | time axis 2025-08-11 to 2025-10-05
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=126888837&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C82 | 7.1 | 로고, 컬러, 폰트 정하기 | 윤이서 | 2025-09-01 | 2025-09-01 | 1 | Done | time axis 2025-08-11 to 2025-10-03
https://github.com/orgs/skn-ai14-250409/projects/70/views/1?pane=issue&itemId=124831683&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C26 | 7.2 | 회원가입/로그인 | 송지훈 | 2025-08-25 | 2025-09-19 | 20 | Done | time axis 2025-08-11 to 2025-10-03
https://github.com/orgs/skn-ai14-250409/projects/70/views/2?pane=issue&itemId=126118090&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C51 | 7.3 | 메인페이지 | 송지훈 | 2025-08-25 | 2025-09-19 | 20 | Done | time axis 2025-08-11 to 2025-10-03
| 8 | Back-end / Infra | time axis 2025-08-11 to 2025-10-05
https://github.com/orgs/skn-ai14-250409/projects/70/views/2?pane=issue&itemId=126185859&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C69 | 8.1 | CI/CD 구축 | 송지훈 | 2025-08-28 | 2025-09-04 | 6 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/2?pane=issue&itemId=125230299&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C28 | 8.1.1 | ⎿초기세팅 | 송지훈 | 2025-08-28 | 2025-09-04 | 6 | Done
https://github.com/orgs/skn-ai14-250409/projects/70/views/2?pane=issue&itemId=126185521&issue=skn-ai14-250409%7CSKN14-Final-4Team%7C68 | 8.1.2 | ⎿database, static 추가 | 송지훈 | 2025-08-28 | 2025-09-04 | 6 | Done
| 8.2 | AWS Infra 구성 | 송지훈 | 2025-08-28 | 2025-09-04 | 6 | Done | time axis 2025-08-11 to 2025-10-05
| 8.3 | 서비스 배포 시스템(Docker) 구축 | 송지훈 | 2025-08-28 | 2025-09-04 | 6 | Done | time axis 2025-08-11 to 2025-10-03
| 8.3.1 | ⎿Docker Volume | 송지훈 | 2025-08-28 | 2025-09-04 | 6 | Done | time axis 2025-08-11 to 2025-10-03
| 8.4 | 서비스 사전 배포 | 송지훈 | 2025-08-28 | 2025-09-04 | 6 | Done | time axis 2025-08-11 to 2025-10-05
| 9 | 테스트 및 개선 | time axis 2025-08-11 to 2025-10-05
| 9.1 | 기능 테스트 | 전원 | 2025-09-22 | 2025-09-26 | 5 | Done | time axis 2025-08-11 to 2025-10-05
| 9.1.1 | ⎿테스트 데이터셋 구축 | 전원 | 2025-09-22 | 2025-09-26 | 5 | Done | time axis 2025-08-11 to 2025-10-03
| 9.1.2 | ⎿테스트 시나리오 작성 | 전원 | 2025-09-22 | 2025-09-26 | 5 | Done | time axis 2025-08-11 to 2025-10-03
| 9.1.3 | ⎿1차 테스트 및 개선점 반영 | 전원 | 2025-09-22 | 2025-09-26 | 5 | Done | time axis 2025-08-11 to 2025-10-03
| 9.1.4 | ⎿2차 테스트 및 개선점 반영 | 전원 | 2025-09-22 | 2025-09-26 | 5 | Done | time axis 2025-08-11 to 2025-10-03
| 9.1.5 | ⎿테스트 계획 및 결과 보고서 작성 | 전원 | 2025-09-22 | 2025-09-26 | 5 | Done | time axis 2025-08-11 to 2025-10-03
| 10 | 배포 | time axis 2025-08-11 to 2025-10-05
| 10.1 | 서버 배포 & 런칭 | 전원 | 2025-09-02 | 2025-09-04 | 3 | Done | time axis 2025-08-11 to 2025-10-05
| 11 | 최종 발표 | time axis 2025-08-11 to 2025-10-05
| 11.1 | 최종 발표 PT 자료 준비 | 전원 | 2025-09-25 | 2025-10-01 | 5 | Done | time axis 2025-08-11 to 2025-10-03
| 11.2 | 시연 영상 촬영 및 업로드 | 전원 | 2025-09-30 | 2025-10-01 | 2 | In progress | time axis 2025-08-11 to 2025-10-03
| 11.2.1 | ⎿시연 영상 시나리오 작성 | 전원 | 2025-09-29 | 2025-09-30 | 2 | In progress | time axis 2025-08-11 to 2025-10-03
Formulas:
소요일 = NETWORKDAYS([계획],G7,holiday!$A1)

## holiday
광복절